## Applicability
Source: | Victor Bogomolov
appturn.com
facebook.com/victor.v.bogomolov
linkedin.com/in/vbogomolov
|  |  | Scrum | Kanban
Team
|  | cross-functional | ü | ?
|  | specialists | û | ü
Project stage
|  | product development | üü | ü
|  | support |  | ü
|  | bugfixing |  | ü
Planning
|  | no backlog ready |  | ü
|  | estimations don't change plans |  | ü
|  | no need to estimae |  | ü
Performance
|  | ability to release anytime |  | ü
|  | ability to change priorities on the fly (responsiveness) |  | ü
|  | productivity and predictability | üü | ü

## Comparison
Source: | Victor Bogomolov
appturn.com
facebook.com/victor.v.bogomolov
linkedin.com/in/vbogomolov
|  | Scrum | Kanban
| Timing | Timeboxed iterations | Timeboxed iterations optional. Can have separate cadences for planning, release, and process improvement. Can be event-driven instead of timeboxed.
| Commitment | Team commits to a specific amount of work for an iteration. | Commitment is optional.
| Default metric for planning and process improvement | Velocity | Lead time
| Team structure | Cross-functional teams | Cross-functional teams optional. Specialists teams allowed.
| Item size | Broken down so they can be completed within 1 sprint | No particular
| Progress chart | Burndown | No particular
| WIP limitations | Indirectly (per sprint) | Directly (per workflow state)
| Estimations | Obligatory | Optional
| Adding new items | No to ongoing iteration | Whenever capacity is available
| Backlog ownership | Sprint backlog owned by a specific team | A kanban board can be shared by multiple teams or individuals
| Roles | PO/SM/Team | No any
| Board persistency | Scrum board reset at each sprint | Kanban board persistent
| Priorities | Product backlog prioritized | Prioritization optional
Lean and Agile
Pull scheduling
WIP limited
Transparency drives process improvement
Focused on delivering releasable software early and often
Based on self-organizing teams
Breaking work down into pieces required
Release plan is continuously optimized based on empirical data (velocity / lead time)
© Kanban & Scrum: Making the most of both : Henrik Kniberg and Mattias Skarin

## to read
http://www.everydaykanban.com/what-is-kanban/
http://www.scrumguides.org/docs/scrumguide/v1/scrum-guide-us.pdf
http://www.solutionsiq.com/what-is-scrumban/
http://www.agilevelocity.com/kanban-vs-scrum-how-to-choose/
http://www.infoq.com/minibooks/kanban-scrum-minibook
https://www.crisp.se/wp-content/uploads/2012/07/Kanban-kick-start-v2.pdf