## Slide 1: PMBoK ed.5
Brief Overview.
Process Flow Perspective.
Compiled by
Oleksiy.Rudenko@gmail.com,
© 2015

## Slide 2: Author
Major expertise:
Business development
Areas of specific expertise:
CRM, Life Insurance, IP, Economics
Project related experience:
Project/program sponsor, manager, contributor, team member
Types of projects completed per scopes:
Product development, Sales development / management / quality, CRM, Operational Excellence, Unification / Standardization
Latest employments:
UNIQA Insurance Group
Oleksiy Rudenko
LL.M., EM, CScM
Inspired by …

## Slide 3: What the PMBoK Guide Is and Isn’t
IS
IS NOT
A generic framework for all project activities
A way to standardize the meanings of all PM terms
A PM methodology
Specific to SW dev
A prescriptive guide on how to manage projects
Need to customize it for your Software Development Life Cycle (SDLC)
PMI not SDLC specific. However see ISSIG

## Slide 4: Baseline Definitions
Project Management
Application of knowledge, skills, tools and techniques to project activities to meet project requirements
Composed of 5 processes:
Initiating
Planning
Executing
Monitoring and Controlling
Closing
Portfolio Management
Collection of projects or programs
Grouped together
Facilitate effective management
Meet strategic business objective
Projects within a portfolio may not have interdependencies
Program Management
Group of related projects
Managed in a coordinated way
Obtain benefits and control
Projects within a program will have interdependencies
PrgM –
PfM – ws

## Slide 5: Baseline Definitions
Projects
Defined objectives. Scope is progressively elaborated throughout project lifecycle
Portfolios
Programs
Scope
Change
Planning
Management
Success
Monitoring
Larger scope & provide more significant benefits
Have a business scope that changes with the strategic goals of organization
Changes are expected and PMs implement processes to keep change managed & controlled
PrgM expects change from both inside & outside and is prepared to manage it
PfM continually monitors change in broader environment
PM progressively & constantly elaborates high-level information into detailed plans
PrgM develops the overall program plan and creates high-level plans to guide detailed planning at component level
PfM creates and maintains processes and communication re aggregate portfolio
PM manages the project team to meet the project objectives
PrgM manages prg staff and PMs; provides vision & overall leadership
PfM manages and coordinates portfolio management staff
measured by product and project quality, timeliness, budget compliance, & customer satisfaction degree
measured by degree to which the program satisfies needs and benefits it was undertaken for
measured in terms of aggregate performance of portfolio components
PM monitors and controls the work of producing products, services & results the project was undertaken for
PrgM monitors the progress of prg components to ensure overall goals, schedules, budget, and benefits of the prg will be met
PfM monitors aggregate performance and value indicators

## Slide 6: PM Processes
Monitoring & Controlling *
Initiating *
Closing *
Planning *
Executing *
* - processes
Mapping to SDLC
Scope
Requirements
Design
Development
Final QA
Implementation
PM Process

## Slide 7: PMBoK Guide Structure
Structured by Knowledge Areas (Subjects of Management)
rather than how project flows
Integration
4
Scope
5
Time
6
Cost
7
Quality
8
HR
9
Communications 10
Risk
11
Procurement
12
Stakeholder
13

## Slide 8: Project-flow-wise approach
Initiating
Planning
Executing
M&C
Closing
Project Integration
Management
4.1
Develop Project Charter
Project Stakeholder
Management
13.1
Identify Stakeholders
Project Integration Knowledge Area coordinates and unifies processes from other Knowledge Areas
Inputs
Project statement of work
Business case
Contract
Enterprise environmental factors
Organizational process assets
Outputs
Project charter
Inputs
Project charter
Procurement documents
Enterprise environmental factors
Organizational process assets
Outputs
Stakeholder register
Stakeholder management strategy

## Slide 9: Project-flow-wise approach
Initiating
Planning
Executing
M&C
Closing
Project Integration
Management
4.2
Develop Project Management Plan
Project Quality Management
8.1
Plan Quality Management
Project HR Management
9.1
Plan HR Management
Project Communications Management
10.1
Plan Communications Management
Project Procurement Management
12.1
Plan Procurement Management
Project Risk Management
11
Project Scope Management
5
Project Time Management
6
Project Cost Management
7.1
Plan Cost Management
7.2
Estimate Costs
7.3
Determine Budget
Project Stakeholder Management
13.2
Plan Stakeholder Management

## Slide 10: Project-flow-wise approach
Project Risk Management
11
Project Scope Management
5
Project Time Management
6
Initiating
Planning
Executing
M&C
Closing
* WBS – Work Breakdown Structure
Project Risk Management
11.1
Plan Risk Management
11.3
Perform Qualitative Risk Analysis
11.2
Identify Risks
11.4
Perform Quantitative Risk Analysis
11.5
Plan Risk Responses
Project Scope Management
5.2
Collect Requirements
5.3
Define Scope
5.4
Create WBS*
5.1
Plan Scope Management
Project Time Management
6.2
Define Activities
6.4
Estimate Activity Resources
6.3
Sequence Activities
6.5
Estimate Activity Durations
6.6
Develop Schedule
6.1
Plan Schedule Management

## Slide 11: Project-flow-wise approach
Initiating
Planning
Executing
M&C
Closing
Project Integration
Management
4.3
Direct & Manage Project Work
Project Quality Management
8.2
Perform Quality Assurance
Project Procurement Management
12.2
Conduct Procurements
Project Communications Management
10.2
Manage Communications
Project HR Management
9.2
Acquire Project Team
9.3
Develop Project Team
9.4
Manage Project Team
Project Stakeholder Management
13.3
Manage Stakeholder Engagement

## Slide 12: Project-flow-wise approach
Initiating
Planning
Executing
M&C
Closing
Project Integration
Management
4.4
Monitor & Control Project Work
Project Procurement Management
12.3
Control Procurements
Project Communications Management
10.3
Control Communications
4.5
Perform Integrated Change Control
Project Scope Management
5.5
Validate Scope
5.6
Control Scope
Project Risk Management
11.6
Control Risks
Project Time Management
6.7
Control Schedule
Project Cost Management
7.4
Control costs
Project Quality Management
8.3
Control Quality
Project Stakeholder Management
13.4
Control Stakeholder Engagement

## Slide 13: Project-flow-wise approach
Initiating
Planning
Executing
M&C
Closing
Project Integration
Management
4.6
Close Project or Phase
Project Procurement
Management
12.4
Close Procurements

## Slide 14: Summary
 | 4 Integration | 5 Scope | 6 Time | 7 Cost | 8 Quality | 9 HR | 10 Communi-cations | 11 Risk | 12 Procurement | 13 Stakeholder
Initiating | Dev charter |  |  |  |  |  |  |  |  | Identify
Planning | Dev PM plan | Plan Collect requirements Define scope Create WBS | Plan schedule mng Def act’v Sequence act’v Estim act’v resources Estim act’v durations Dev schedule | Plan Estimate Determine budget | Plan | Plan | Plan | Plan Identify Quali RA Quanti RA Plan risk responses | Plan | Plan
Executing | Direct & manage prj work | Validate |  |  | Perform Q assurance | Acquire PT Develop PT Manage PT | Manage |  | Conduct | Manage SH engagement
M&C | M&C prj work | Control | Control schedule | Control | Control |  | Control | Control | Control | Control SH engagement
Closing | Close prj or phase |  |  |  |  |  |  |  | Close | 
Initiating | 
Planning | 
Executing | 
M&C | 
Closing | 

## Slide 15: Summary
 | 9 HR | 10 Communi-cations | 11 Risk | 12 Procurement | 13 Stakeholder
Initiating |  |  |  |  | Identify
Planning | Plan | Plan | Plan Identify Quali RA Quanti RA Plan risk responses | Plan | Plan
Executing | Acquire PT Develop PT Manage PT | Manage |  | Conduct | Manage SH engagement
M&C |  | Control | Control | Control | Control SH engagement
Closing |  |  |  | Close |